# Three-Month Completion Plan for 60 ECTS Thesis

This plan outlines the structured steps to complete the remaining work on the Iceland Earthquake Monitoring thesis project within 3 months. The website is already near completion; the main focus now is on finalizing code understanding, documentation, and writing the thesis chapters including literature review.

## Phase 1: Code Understanding and Final Adjustments (Weeks 1–3)

- Fully review backend (Flask, Scraper, Database) and frontend (React, Map, Slider, Components) code.
- Document workflow and data flow diagrams.
- Fix minor bugs or polish UI/UX if required.
- Prepare short technical notes explaining how each module works (to be reused in thesis chapters).
- Draft Chapter 4: Backend (scraping, database, API).
- Draft Chapter 5: Frontend (map visualization, filtering, user interface).

## Phase 2: Thesis Writing and Chapters Drafting (Weeks 4–8)

- Write Introduction & Problem Statement (Chapter 1).
- Write Related Work (Chapter 2) based on initial papers.
- Write Methodology (Chapter 3): system architecture, technologies, design decisions.
- Expand Chapter 4 (Backend) and Chapter 5 (Frontend) with technical explanations and screenshots.
- Include diagrams: Architecture Diagram, Database Schema, Component Flow.
- Internal review of written chapters (self + supervisor feedback).

## Phase 3: Literature Review & Research Contribution (Weeks 5–10)

- Collect academic papers on earthquake visualization (GIS, Google Maps, Leaflet, D3.js, WebGL, VR/AR methods).
- Summarize visualization techniques and compare to own system.
- Write detailed Literature Review (Chapter 2 expanded).
- Position thesis contribution in relation to existing methods.
- Identify potential for journal/conference publication.

## Phase 4: Evaluation, Validation, and Stakeholder Feedback (Weeks 9–11)

- Test system with sample users and edge cases.
- Visit Icelandic Meteorological Office to present tool.
- Gather qualitative feedback (usability, scientific value).
- Document evaluation results (Chapter 6).
- Write Discussion on strengths, limitations, and future work.

## Phase 5: Finalization and Defense Preparation (Weeks 11–12)

- Write Conclusion and Future Work (Chapter 7).
- Complete Abstract, References, and Appendices.
- Proofread entire thesis (language, formatting, citations).
- Prepare defense presentation (slides, demo of system).
- Practice with supervisor/peers for Q&A.
- Submit final thesis and defend.

## Key Milestones

Week 3 – Backend/Frontend chapters drafted.
Week 6 – Methodology + Introduction completed.
Week 8 – Literature Review drafted.
Week 10 – Evaluation and stakeholder feedback.
Week 12 – Final submission and defense.