📅 Suggested Timeline Plan (16 Sept – 1 Dec)

Phase 1 – Foundation (16–30 Sept)

- ✅ Start documentation rewrite using Overleaf.

- Compare old documentation with new system → mark obsolete sections (e.g., Folium, CSV).

- Draft Chapter 3 (Backend) & Chapter 4 (Frontend) with the current architecture.

- Prepare System Overview diagrams:

  - Architecture (Scraper → DB → API → Frontend).

  - DB schema (earthquake + volcano).

  - Component diagram (Map, Slider, Scale, Cross-section, DeepQuakes, Footer, About).

- Begin literature review reading (collect at least 10–15 papers on: earthquake visualization, real-time monitoring systems, seismology web platforms, GIS).

Phase 2 – Core Documentation (1–15 Oct)

- Write Chapter 2 (Project Overview) updated with Google Maps + React system.

- Write Chapter 5 (Frontend) fully (Map, Time Slider, Mag Scale, Volcanoes, DeepQuakes, Cross-section).

- Write Chapter 6 (Improvements & Challenges) based on what you solved (APScheduler context, auto-refresh, hover removal, etc.).

- Parallel: Summarize literature review notes (short bullet summaries → to be expanded in Nov).

- Deliverable by mid-Oct: 50–60% of thesis text drafted.

Phase 3 – Advanced Content (16–31 Oct)

- Write Chapter 7 (Future Development): predictive models, PostgreSQL, machine learning, cloud deployment.

- Write Chapter 8 (Deployment & Testing): Pluto server + Gunicorn process + auto-refresh polling + challenges.

- Update Conclusion & Abstract to reflect new version.

- Draft literature review chapter (~10 pages).

- Start writing paper draft (shorter, ~6–8 pages, conference style).

Phase 4 – Finalization (1–15 Nov)

- Finish Chapter 9 (Final Features) with polished feature list (map layers, depth toggle, magnitude scale, cross-section).

- Finish Chapter 10 (Conclusion).

- Insert references (APA/IEEE format).

- Full thesis draft complete by 15 Nov.

- Share with supervisor for feedback.

Phase 5 – Review & Delivery (16 Nov – 1 Dec)

- Revise thesis after feedback.

- Polish figures, tables, diagrams.

- Finalize literature review.

- Prepare presentation slides for defense.

- Finalize paper submission draft.

- By 1 Dec → Thesis ready, paper draft complete, demo app stable for Met Office.

📌 Weekly Milestones

- Week 1 (Sept 16–22): Rewrite backend & frontend chapters (Overleaf), start diagrams.

- Week 2 (Sept 23–29): Literature collection + overview chapter.

- Week 3 (Sept 30–Oct 6): Frontend & improvements chapter done.

- Week 4 (Oct 7–13): Challenges & deployment writing.

- Week 5 (Oct 14–20): Literature review draft.

- Week 6 (Oct 21–27): Future work + testing chapter.

- Week 7 (Oct 28–Nov 3): Conclusion + abstract rewrite.

- Week 8 (Nov 4–10): Paper draft writing.

- Week 9 (Nov 11–17): Supervisor review, corrections.

- Week 10 (Nov 18–24): Full thesis polish.

- Week 11 (Nov 25–Dec 1): Final submission & defense prep.